## Slide 1: Planning and future activities
Cydalise Dumesnil for the MAJIS team

## Slide 2: MASTER SCHEDULE
Spacecraft constraints:
Integration to be done for the TB/TV test at spacecraft level
Avoid the opening of spacecraft vault for the integration/ exchange of the electronic units after the TB/TV
Instrument constraints:
Procurements delays : electronic components
Radiator paint change
Calibration activities performed with FS electronic unit
Additional test activities

## Slide 3: MAJIS KEY MILESTONES WITH SPACECRAFT
 |  | Current dates | ESA expected dates (ICDR)
Review | MAJIS software CDR | CCSW : Nov. 19 MSW : End of Feb. 20 | Shall be compatible with the ME-PFM delivery
Hardware | ME-PFM delivery | 24/07/20 | 01/08/20
Hardware | OH-STM-R delivery | 24/07/20 | 01/08/20
Hardware | OH –PFM calibration with ME-FS | 19/01/20-15/03/21 | N/A
Hardware | OH-PFM delivery | 18/03/21 | 22/02/21

## Slide 4: COMBINED ACTIVITIES
OH PFM in minimum configuration for E2E with ME
ME ready for E2E
OH STM-R
02/07/2020
OH
ME PFM
OH PFM final integration
E2E test :
FFT at cold temperature
OH STM-R + ME PFM functional test
ME incoming and installation
ME and OH STM-R packing
24/07/2020
MAJIS
S/C
TB/TV test
@LDO premices

## Slide 5: FUTURE ACTIVITIES
OH STM-R:
Final procurement
Start of assembly beginning of December
OH PFM :
FPU characterization
ME PFM:
PE and Aux FPGA finalization (Anti-fuse FPGA)
Software CDR

## Slide 6: MAJIS VALIDATION FLOW CHART
ME FS 02/11/2020
31/12/2020
OH
ME FS
OH PFM final integration 13/11/2020
EMI-EMC test
Calibration
FFT
10 days
18/03/2021
GSE
Calibration facility GSE ready 12/11/2020
19/11/2020
@IAS premices

## Slide 7: FUTURE ACTIVITIES
CALIBRATION FACILITY :
Thermal vacuum validation
Optical bench validation
Test sequences preparation
OH PFM:
FM Detector characterization:
  VIS-NIR channel at IASB
  IR channel at IAS
Spectrometer and telescope alignment
Scan mirror test

## Slide 8: CONCLUSION
STM-R and PFM activities in parallel
High pressure on schedule and low margins
Remaining uncertainties but supervision
  Procurement delivery dates not completely confirmed
  OH-PFM radiator paint